Contents

Summary	3

Scope	3

References	3

Quality Assurance	3

Definitions, Acronyms and Abbreviations	4

Project Classification	5

Class Definitions	5

Class Requirements	5

Classification Authority	6

Requirements by Class	6

Universal Requirements	7

Document Classification System	7

Three Document Types	7

Client and Company Conflicts	7

Electronic Document Management System	7

SharePoint	8

Network Server (i-drive)	10

Master Document Register	10

Updating the MDR	11

Document Metadata	11

Document Numbering Specifications	12

Document Title	13

Document Revision	13

Document Revision Date	14

Issue Status Codes	14

Return Status Codes	15

Transmittal	15

Security Classification	15

Creation of Documents	16

Document Number Assignment	16

Templates	17

Quality Control/Assurance	18

Transmittal of Documents	19

Request to Transmit	19

Outgoing	20

Incoming	20

Email Notifications	20

Revision and Approval	21

Distribution of Documents	21

Adobe Cloud Review	21

Bluebeam Sessions	22

Data Inventory	23

Appendix A: Document Numbering Schematic	24

Format Structure	24

Market Documents	25

Appendix B: Discipline Codes	26

Appendix C: Document Type Codes	27

Appendix D: Return Status Codes	28

Appendix E: Project Class Requirements	29

Attachment 1: Internal Review Cycle	30

Attachment 2: Deliverable Review Cycle	31

## Summary

The purpose of this document is to provide guidance on the concepts and processes of document control that are important for, and have impact on, the performance of Market projects and Company’s business operations within Market.

This procedure defines the requirements for the creation, review, approval, distribution, use and revision of documentation for all Market projects where Information Management/Document Control (IM/DC) services may or may not be directly involved.

This procedure applies to all Market projects and serves as the minimum standard that all Market projects shall follow. Procedures are designed for ultimate simplicity while building good document management habits that prepare project teams for more complex requirements.

## Scope

## References

### Quality Assurance

#### 3000 - Procedure

- QUAL3090 - Preparation & Review of Technical Calculations

- QUAL3091 - Review of Technical Drawings

- QUAL3092 - Preparation & Review of Technical Documents

- QUAL3093 - Review of Construction Contract Submittals - Traditional & Nontraditional

- QUAL3094 - Review of Construction Contract Delegated Design Submittals - Traditional and Nontraditional

- QUAL3110 - Control of Client/Contract/Project-Specific Quality Assurance Documents

- QUAL3120 - Control of Nonconformance

- QUAL3130 - Control of Project Records

- QUAL4000 - Quality Manual

#### Forms

- QUAL3090.01 - Review of Technical Calculations/Technical Documents

- QUAL3091.01 - Manager Review of Drawings

- QUAL3092.01 - Review of Technical Calculations/Technical Documents

- QUAL3093.01 - Log of Submittals

- QUAL3093.02 - Traditional Review of Construction Contract Submittals

- QUAL3093.03 - Nontraditional Review of Construction Contract Submittals

- QUAL3094.01 - Log of submittals

- QUAL3094.02 - Traditional Review of Delegated Design Submittals

- QUAL3094.03 - Nontraditional Review of Delegated Design Submittals

- QUAL3110.01 - Review, Approval and Posting Record

## Definitions, Acronyms and Abbreviations

- Access Log - A log displaying all project personnel who have access to EDMS, their access privileges, the company to which they are employed, and an email address.

- Client - company with which project contract has been signed.

- Company: Hanson Professional Services, Inc.

- Controlled Document: A document that goes through internal review cycles but not submitted to Client.

- CQAP: Corporate Quality Assurance Program

- Deliverable: A document subject to continuous updating for which an ongoing record of its distribution and receipt (at all revision levels) is maintained on Client’s behalf.

- Document Control (DC): Responsible for performing quality assurance and checks on all controlled documentation.

- Document Distribution Matrix (DDM) - A lookup table showing a relationship between project personnel and the document types to which they will receive notifications.

- Electronic Document Management System (EDMS): Data and documentation repository such as SharePoint. Network drives shall not be considered an efficient nor satisfactory EDMS.

- IM/DC: Information Management/Document Control services. Falls under the INF discipline.

- Issue Status Code (ISC): Industry-standard codes identifying the status of document review cycles.

- Main Information Contractor (MIC): A centralized service on Client’s behalf to facilitate all angles of document management. Client and all subcontractors shall use Market EDMS or other review tools through document lifecycle.

- Market - The Industry market within Company.

- Master Document Register - A complete listing of all controlled documentation. For Class II and Class III projects, MDR shall maintain separate registries for Client and Market documentation.

- O: Originator - person who creates the document.

- POR: Professional of Record - professional licensed to practice in the jurisdiction who provides final approval.

- QCR: Quality Control Report - audit trail documentation from review sessions.

- TM: Task Manager - person responsible for managing review sessions prior to POR approval.

- Uncontrolled Document: Supporting documents that exist without formal QA/QC review processes.

## Project Classification

### Class Definitions

Class I - Small-Scale Projects

Small-scale projects with limited scope and complexity requiring minimal external stakeholder coordination. Market staff handles all document control tasks independently without Information Management/Document Control (IM/DC) personnel involvement.

Class II - Standard External Review Projects

Standard projects involving external review sessions with Client requiring moderate complexity and IM/DC support. These projects involve coordination between Company and Client document management systems with multiple stakeholder involvement.

Class III - Main Information Contractor Projects

Complex projects where Market acts as Main Information Contractor (MIC) with comprehensive responsibility for all document control and information management aspects. Client has minimal IM/DC processes, requiring Market to establish and maintain complete document management systems.

### Class Requirements

All aspects of this procedure shall be considered required unless otherwise indicated. In this manner, a table will lead the section identifying if the section is applicable to the class project

- Not Applicable: The subject topic is not applicable to documentation of the respective Project Class

- Best Practice: The subject topic should be followed to encourage consistency, but is not required.

- Required: The subject topical shall be followed unless Client specifications declare otherwise.

| Class | Required | Best Practice | Not Applicable |
| --- | --- | --- | --- |
| Class I |  |  | x |
| Class II |  | x |  |
| Class III | x |  |  |

Table 1: Example table of class requirements

### Classification Authority

The Project Manager (PM) and Market Principal (MP) shall determine project classification during project initiation.

### Requirements by Class

Class I Requirements

- No EDMS requirements

- No IM/DC personnel involvement

- Store all project documents on Company network drive

- Follow O → TM → POR review cycle via Bluebeam (see Attachment 1)

- Maintain detailed tracking and documentation of all review activities

- Apply Security Classification system (default “Restricted”)

Class I Best Practices

- Implement Issue Status Codes for enhanced tracking

- Use formal revision numbering system

- Maintain audit trail documentation

Class II Requirements (extends Class I)

- IM/DC services support required

- Mandatory implementation of Issue Status Codes

- Formal revision tracking and documentation

- Comprehensive audit trail requirements

- External stakeholder coordination protocols

- SharePoint for deliverables management and version control

- Integration with Client EDMS as required

- Dual metadata systems when Client requirements conflict with Company requirements

Class III Requirements (extends Class I)

- Complete IM/DC team involvement and oversight

- Complete document management system implementation

- Advanced metadata tracking and reporting

- Complex review workflows with multiple stakeholder coordination

- Comprehensive audit trail and compliance documentation

- Full SharePoint implementation with advanced workflows

- Custom reporting and dashboard capabilities

- Integration with multiple stakeholder systems as required

### Universal Requirements

All project classes shall maintain:

- Universal review process via Bluebeam

- Company document numbering format compliance

- Security Classification system implementation

## Document Classification System

| Class | Required | Best Practice |  | Not Applicable |  |
| --- | --- | --- | --- | --- | --- |
| Class I | x |  |  |  |  |
| Class II | x |  |  |  |  |
| Class III | x |  |  |  |  |

### Three Document Types

- Uncontrolled Documents: Supporting documents without formal QA/QC review

- Controlled Documents: Undergo internal review cycles but not submitted to Client (may turn into Deliverables)

- Deliverables: Thorough review process, submitted to Client on a scheduled basis

#### Uncontrolled Documents

Uncontrolled documents are documentation generally retrieved from external resources but does not undergo a QA/QC review process. Such examples may be a catalog, brochure, pamphlet, reference drawing, sketches, etc.

#### Uncontrolled documentation may be attached to Controlled documentation as supporting evidence but generally shall not be kept on the network drive or treated as a controlled document or deliverable.

#### Controlled Documents

Controlled documents are formally managed documentation that is considered vital to the project lifecycle. This documentation may undergo formal QA/QC review processes but would not be considered a Deliverable to Client.

Such examples of this type of documentation would be correspondence (emails between Company and Client), meeting minutes, internal procedures, templates, bids, proposals, RFQs, etc.

Controlled documentation shall be kept in project EDMS when applicable to ensure project team members are always working from the most recent approved version. Working from controlled documentation outside of an EDMS is inherently risky and by definition considered uncontrolled.

#### Controlled documents shall be retained on the network drive in any location with the exception of the ./Admin/17-Deliverables folder.

#### Deliverables

Deliverables are documentation that shall be submitted to Client to meet project requirements. As Controlled documents undergo QA/QC processes, so do Deliverables. The exception is that Deliverables must be reviewed and approved by Client.

The document metadata associated with Deliverables is generally set by Clients, especially for Class II projects. For Class III projects, if Client does not provide information management or document control procedures or specifications, Market DC shall ensure documentation may easily be differentiated as having originated from Client or Company.

Deliverables shall be kept in the ./Admin/17-Deliverables folder only.

## Client and Company Conflicts

| Class | Required | Best Practice |  | Not Applicable |  |
| --- | --- | --- | --- | --- | --- |
| Class I |  | x |  |  |  |
| Class II | x |  |  |  |  |
| Class III |  | x |  |  |  |

Every controlled document shall have a Market Document Number assigned along with Market metadata. Client specifications are applicable only towards Deliverables.

Where metadata terms may conflict, the metadata shall be differentiated between Company and Client, respectively. For example, Company Document Number and Client Document Number would be two different metadata tags.

Deliverables are not required to have a Company Document Number or other Company metadata assigned. Unless otherwise specified, only Client metadata shall be printed on the deliverable.

## Electronic Document Management System

| Class | Required | Best Practice |  | Not Applicable |  |
| --- | --- | --- | --- | --- | --- |
| Class I |  | x |  |  |  |
| Class II | x |  |  |  |  |
| Class III | x |  |  |  |  |

An Electronic Document Management System (EDMS) is a location where data and documentation related to specific projects is stored for access by project members. Unless otherwise specified, the chosen EDMS for Market projects shall be a single SharePoint 365 Site (SharePoint). The EDMS shall be set up to utilize the built-in functionality of SharePoint without the use of 3rd party resources. However, 3rd party resources may be used to build reports and dashboards and conduct audits on a scheduled basis.

All deliverables shall be stored in the Deliverables library within SharePoint. Additional folders may exist within the Deliverables library based on confidentiality requirements.

The EDMS shall be considered the sole source of truth for Project data and documentation. Any data or controlled documents not within the EDMS shall be considered obsolete and out of date.

All documentation within the EDMS shall contain a Document Number. With the exception of transmittals, all documentation shall also have a Document Revision, Document Revision Date, and Issue Status Code. Additional metadata may also be populated to aid in identifying and differentiating deliverables, as well as provide scheduling details.

### SharePoint

Unless otherwise specified, SharePoint is the chosen EDMS for Project-controlled documentation. SharePoint allows the creation of document libraries along with storing relevant metadata for each document. All deliverables shall be stored in the EDMS. All documents shall also have required metadata fields as listed in Document Metadata populated.

Any deliverable not in EDMS shall be considered unreliable and out-of-date.

Every deliverable shall have a filename identical to it’s document number. Only alphanumeric, dash, and space characters are permitted.

Every document shall be in native format. Once a document is finalized for an internal review cycle, an identical PDF must be produced and stored in EDMS. All metadata, regardless of file format, must be identical per document.

#### Libraries

##### Controlled

##### Deliverables

Deliverables is a EDMS folder (henceforth referred to as “Library”) considered the primary repository for all deliverables within EDMS. Library shall contain all controlled project deliverables and associated documentation (i.e., transmittals, reviewed deliverables, etc.).

See Document Metadata for required metadata that shall be tracked and maintained.

#### Versioning

Library must have versioning enabled, including minor versioning.

Major versioning uses natural numbers (i.e., 1, 2, …,  ∞). Major versioning shall be used to identify when a new revision has been released for transmittal to Client, or when a deliverable review period has ended and comments closed.

Minor versions are those which SharePoint tracks to monitor changes to a deliverable between major revisions. Minor versions are rational numbers (i.e., 0.1, 0.2, 1.1, 1.2, 1.3, …,  ∞).

Versioning shall not be confused with a revision; both fields are independent. Version numbers are a SharePoint tag simply used to track the entire history of a document regardless of review cycles.

##### Minor Versions

Minor versions are kept to record changes to a document or its metadata in between revision cycles. Such metadata could be forecast issue dates, document title modifications, or other metadata that does not directly impact the status of a document. A document with a minor version (e.g., 0.4, 1.3, 3.9, etc.) is a document that has been revised since it’s last official release and shall be considered “NOI” - Not Officially Issued.

When a document has been transmitted the version history shall be flattened to preserve storage space unless project specifications require maintaining this history.

#### Access

Access shall be granted based on the Class of a project and Security Classification of the document. The staff of Clients, Contractors, and Subcontractors may be granted access as requested by Project management.

Project Document Control shall create an Access Log, treated as a controlled document. This log shall be maintained by Document Control to identify user access including names, email addresses, level of confidentiality and other contact information.

By default, users should be added as a Visitor for read-access only.

The Information Management team shall be given Admin rights to SharePoint, or as Hanson IT policy permits. Outside of Information Management, no member shall have privileges beyond read-access in order to protect the integrity of SharePoint.

#### Checking Out and Checking In a Document

Members with read-only access are unable to check out documentation.

##### Publishing Deliverables

When a deliverable is transmitted the document must be published to create a major version. A published document must contain the transmittal to which the document and it’s respective revision belong.

### Network Server (i-drive)

Deliverables stored within SharePoint shall be backed up on Project’s shared drive, commonly referred to as the i-drive. This folder, “17-Deliverables”, is located directly under the Admin directory within the project folder.

Directory “17-Deliverables” shall have subdirectories for each transmittal incoming and outgoing between Company, Client, and any Contractors or Subcontractors, even if they are not Deliverables required by Market. This folder shall contain the native and PDF version of the officially transmitted document. Where a transmittal is required by the project, the transmittal shall also be made available.

The email from the POR authorizing transmittal of the documents shall exist in PDF format.

The email notifying Company on successful transmittal of the documents shall exist in PDF format.

Depending on Client’s transmittal requirements, an email may exist notifying Client of a new transmittal. This email shall also be saved in the transmittal directory in PDF format.

#### Folder Organization

Required folder structure:

[SUBJECT folder]/[Discipline Code]/[Document Number]/[Revision or Status]/

Example:

01-Project Management/PMG/PRJ-PMG-RPT-241215/RevA/
13-Calculations/MEC/PRJ-MEC-CAL-241220/RevA/
11-Plans/CIV/PRJ-CIV-DWG-241218/Rev0/

## Master Document Register

| Class | Required | Best Practice |  | Not Applicable |  |
| --- | --- | --- | --- | --- | --- |
| Class I |  | x |  |  |  |
| Class II | x |  |  |  |  |
| Class III | x |  |  |  |  |

A Master Document Register (MDR) shall be created and maintained by Project DC. The MDR shall list all Deliverables planned and submitted to Client. Best practice is the MDR should be a full export via Microsoft Excel that is readily available for internal project personnel (see Data Inventory).

MDR shall list all Deliverables, regardless of confidentiality, along with all metadata identified in the MDR. DC shall perform audits on a weekly basis to ensure Deliverables are listed in both Library and the MDR, and that metadata is identical.

### Updating the MDR

Library shall be considered the most up-to-date register for all deliverables across the project. The MDR shall be considered a snapshot of EDMS.

## Document Metadata

| Class | Required | Best Practice | Not Applicable |
| --- | --- | --- | --- |
| Class I |  | x |  |
| Class II | x |  |  |
| Class III | x |  |  |

- File Name

- Document Number

- Document Title

- Revision

- Revision Date

- Issue Status Code

- Transmittal

- Transmittal Date

- Due Date

- Project Code

- Discipline Code

- Document Type Code

- POR

- TM

### Document Numbering Specifications

All controlled documents shall utilize a standardized numbering system that provides systematic identification, organization, and tracking throughout the document lifecycle. This numbering system applies exclusively to Market-created documentation and does not extend to external party documents, which retain their original numbering schemes. See Appendix A.

#### Purpose and Benefits

The standardized numbering system serves multiple critical functions:

- Unique identification of every Market document within the project environment

- Systematic organization by discipline, document type, and creation sequence

- Audit trail support for document lifecycle tracking and compliance requirements

- Integration capability with Data Warehouse tools and document management systems

- Efficient retrieval through structured search and filtering capabilities

#### Universal Format Application

All Market projects shall utilize the same document numbering format regardless of project classification. This approach eliminates complexity variations between project classes while maintaining systematic organization benefits across all Market activities.

#### Sequential Number Management

Document sequential numbers shall be assigned using Data Warehouse tools or systematic network drive review to ensure integrity and prevent conflicts.

Sequential numbers shall follow discipline-specific implementation:

- Numbers shall be unique within each discipline/document type combination

- Numbering shall begin at 0001 for each discipline/document type combination

- VOID document numbers shall never be reused under any circumstances

- CAN document numbers shall not be reused for operational simplicity

- Sequential gaps from retired numbers remain permanent in the numbering system to avoid potential complications through project maturity.

#### Lifecycle Consistency

Document numbers shall remain constant throughout the document lifecycle regardless of revision status, Issue Status Code changes, or project classification modifications. This consistency ensures reliable document identification and audit trail maintenance.

External party documents maintain their original numbering systems and are tracked through existing Company submittal and correspondence management processes as defined in applicable QUAL procedures.

Complete format specifications, code definitions, and sequential numbering rules are provided in Appendix A.

### Document title

Document title may contain one or more of the following characters:

- Alpha [a-zA-Z]

- Numeric [0-9]

- Punctuation [-_]

- Spaces [ ]

No additional characters shall be used as they may corrupt other software or database systems.

### Document Revision

Document revisions shall follow industry-standard practices based on document status and review requirements.

#### Alpha Revisions

Alpha revisions shall be used for documents in review cycles:

- Sequence: A, B, C, D, E, F, G, H, J, K, L, M, N, P, Q, R, S, T, U, V, W, X, Y, Z

- Letters I and O shall not be used to prevent confusion with numbers

- If revisions exceed Z, continue with AA, AB, AC, etc.

#### Numerical Revisions

Numerical revisions shall be used for approved documents:

- Sequence: 0, 1, 2, 3, 4, 5, 6, 7, 8, 9

- Begin with 0 for first approved version

- Increment sequentially for subsequent approved versions

#### Mixed Revisions

Mixed revisions shall be used when approved documents require re-review:

- Format: [Number][Letter] (e.g., 0A, 1B, 2C)

- Combines numerical base with alphabetic increment

- Used when documents return to review cycle after approval

#### Revision Assignment Rules

- No revisions shall be skipped in sequence

- Each document type follows specific revision patterns based on Issue Status Code requirements (see Issue Status Codes)

### Document Revision Date

Document revision dates shall be printed in YYYY-MM-DD format where

- YYYY - four-digit year

- MM - two-digit month

- DD - two-digit date

### Issue Status Codes

The following Issue Status Codes shall be used to identify document review status:

| Code | Description | Revision Format | Usage |
| --- | --- | --- | --- |
| PLN | Planned | N/A | Documents scheduled for creation but not yet drafted |
| DFT | Draft | Alpha | Documents in development phase |
| IFI | Issued for Information | Alpha | Documents providing information without requiring action |
| IFE | Issued for Estimate | Alpha | Documents supporting cost estimation activities |
| IFR | Issued for Review | Alpha | Documents formally distributed for review |
| IFA | Issued for Approval | Alpha | Documents ready for final approval after review |
| IFU | Issued for Use | Numerical | Documents approved for operational use |
| APP | Approved | Numerical | Documents with formal approval status |
| IFH | Issued for HAZOP | Alpha | Documents approved for HAZOP study activities |
| IFD | Issued for Design | Alpha | Documents released for design development |
| IFC | Issued for Construction | Numerical | Documents approved for construction activities |
| ASB | As Built | Numerical | Documents reflecting actual constructed conditions |
| SUP | Superseded | Next sequential | Documents replaced by newer versions |
| CAN | Cancelled | N/A | Documents no longer required (metadata tracking only) |
| REJ | Rejected | Alpha | Documents returned for revision after review |
| VOID | Void | Numerical | Documents formally voided and withdrawn |

#### Issue Status Code Rules

- CAN status is used for metadata tracking only and shall not be issued as a document revision

- VOID document numbers shall never be reused under any circumstances

- Typical document progression follows: PLN → DFT → IFR → IFA → APP

- APP usage depends on client requirements and project specifications

### Return Status Codes

Return Status Codes identify client approval status for submitted documents. These codes shall be used when tracking client review responses:

| Code |  | Description |  | Typical Action |
| --- | --- | --- | --- | --- |
| Code 1 |  | Approved |  | Document may proceed to next Issue Status Code or remain as submitted |
| Code 2 |  | Approved with comments |  | Document may proceed but comments should be incorporated in future revisions |
| Code 3 |  | Rejected |  | Document requires revision and resubmittal |
| Code 4 |  | No review required |  | Document accepted without formal review process |
| Code 5 |  | VOID |  | Document formally voided by client |

#### Return Status Code Application

- Return Status Codes apply only to documents submitted for external review

- Code 1 and Code 4 typically allow progression to next Issue Status Code

- Code 2 and Code 3 typically require document revision and resubmittal

- Code 5 requires document voiding and potential replacement document creation

### Transmittal

### Security Classification

Each controlled document shall be assigned to a Security Classification. This Security Classification identifies storage location, distribution requirements, and access permissions.

#### Security Classification Codes

| Classification | Definition |
| --- | --- |
| Unrestricted | Document can be shared within Client and other 3rd parties |
| Restricted | Document can be shared within Client |
| Confidential | Document can be shared within market |
| Most Confidential | Document is highly confidential and can only be stored in a repository specially configured for that purpose. Access confined exclusively to project team members |

#### Default Classification

All project documents shall default to “Restricted” classification unless otherwise specified by Project Management or Client requirements.

Security Classification shall be clearly identified on the drawing or cover page of the document.

## Creation of Documents

### Document Number Assignment

Every Controlled document shall have a Company Document Number. This document number shall be provided by Document Control unless otherwise noted in Client procedures or specifications. If a new document is being produced and that document is not listed in the MDR, Project personnel shall submit a request for a new document number via email to documentcontrol@hanson-inc.com. Document numbers shall only be assigned by Market Document Control.

### Templates

All documents shall have clearly identified Company Document Number, Company Document Revision, Company Revision Date, Revision History (up to three revisions), Company Issue Status, and Security Classification Code. Equipment tag numbers, if available, shall also be clearly identified.

For Class II projects, Client metadata shall be used in place of Company metadata, i.e., Client Document Number, Client Document Revision, etc.

Templates have been created to enable authors to immediately begin drafting a document. They may be found in the Project’s shared i-drive or the Documents library in SharePoint.

Each template contains the required metadata for this project on the cover page. In addition, headers and footers should also be updated appropriately to reflect the required metadata.

#### Microsoft Word Template

Authors shall download the selected template to their working directory. From there, the following edits shall be made to the document.

- Rename the file to the respective document number.

- Edit the header of the document a.     With file open, select the “Insert” ribbon b.     Click the down arrow under “Header” in the “Header & Footer” pane. c.     Select “Edit Header”. i.    There are two headers to update; both largely repetitive. 1. Update Document title 2. Update Document Number 3. Update Security Classification per MDR or Site 4. Update Export Code per MDR or Site ii.    Update the revision block in the footer on the cover page. The revision block shall be contained to no more than three rows with the most recent revision listed first. 5. Revision 6. Issue Status 7. Originator 8. Reviewer 9. Approver 10. (Revision) Date iii.    Click “Close Header and Footer”

- On cover page, update Document Title

- From pg. 3 forward document contents can be deleted and replaced with the contents of the true document.

When the document is complete, the discipline lead may place the document in the Project’s shared i-drive within the respective subject folder. Originator shall then email a link to the folder to documentcontrol@hanson-inc.com for review and release.

#### Microsoft Excel Template

Authors shall download the selected template to their working directory. From there, the following edits shall be made to the document.

- Rename the file to the respective document number.

- On the cover page, update a.     Document Title in K1 and A19 b.     Document Number in K2 c.     Security Class in K3 d.     Export Code in R3 e.     Revision block. The revision block shall be contained to no more than three rows with the most recent revision listed first. i.    Revision ii.    Issue Status iii.    Originator iv.    Reviewer v.    Approver vi.    (Revision) Date

- On each worksheet (with the exception of the cover page), a.     Select “Page Layout” in the ribbon panel. b.     Click the arrow icon in the lower-right of the Page Setup pane. c.     Select the “Header/Footer” tab d.     Make sure the following selections are enabled: i.    Different first page ii.    Scale with document iii.    Align with page margins e.     Select “Custom Header” f.      With the Header tab selected, and in the “Right section” window, add i.    Document Number ii.    Document Revision iii.    Revision Date

When the document is complete, the discipline lead may place the document in the Project’s shared i-drive within the respective subject folder. Originator shall then email a link to the folder to documentcontrol@hanson-inc.com for review and release.

#### Microsoft Visio Template

A generic Microsoft Visio template is also. Authors shall download the template to their working directory. From there, the following edits shall be made to the document.

- Rename the file to the respective document number.

- On the cover page, update a.     Document title in upper-right corner, and document title in center of the page b.     Document Number in upper-right corner c.     Security Class in upper-right corner d.     Export Code in upper-right corner e.     Revision block. The revision block shall be contained to no more than three rows with the most recent revision listed first. i.    Revision ii.    Issue Status iii.    Originator iv.    Reviewer v.    Approver vi.    (Revision) Date

Visio does not have headers and footers as Word and Excel do. Instead, the template uses a background drawing. In the template provided, the background is found on the tab “Border”. This border must be edited as well for subsequent pages beyond the cover page. Only the top portion of the border shall be edited to match the data on the cover page.

When the document is complete, the discipline lead may place the document in the Project’s shared i-drive within the respective subject folder. Originator shall then email a link to the folder to documentcontrol@hanson-inc.com for review and release.

## Quality Control/Assurance

DC shall validate the data per Project specifications and, if necessary, communicate with POR any conflicts. If all metadata meets standards, the document shall be uploaded into EDMS and considered the latest release. DC shall update metadata in Library, as necessary and, on completion, publish the final version. DC shall add a note of the transmittal number to the Publish comments.

If document does not meet quality standards document is to be considered “rejected” and returned to RE for correction.

When a deliverable is received from Client, DC shall perform a quality review analysis. On approval, DC shall place the deliverable into the DMS, updating metadata as required, publish the document with the incoming transmittal number, and with the DDM, email links to the new/revised documentation to Company. On disapproval, DC shall reject the transmittal and return to Client.

## Transmittal of Documents

### Request to Transmit

When a document revision draft has been completed, Originator shall review the document one final time to ensure the following:

- Metadata is present on the cover page of a document or in the title block of a drawing

  - Client document number

  - Document Title

    - Titles shall not contain symbols beyond hyphens, periods, parentheses, brackets, colons, and semi-colons.

    - Titles shall be title-case with the exception of acronyms which may be upper-case.

  - Client Document Revision (Reference Appendix 3)

    - Documents Issued for Review shall begin with revision A.

    - Documents Issued for Information shall begin with revision 0.

    - Approved documents that have undergone a review cycle shall begin with revision 0.

  - Issue Status Code (Reference Appendix 4)

  - Issue Date in MM/DD/YYYY format.

  - Security Class (Reference Appendix 5)

- Sheet numbers shall not be included. Each drawing shall be submitted as its own drawing, sharing the same title with the exception the title is appended with ” - Sheet x of y”.

- For drawings, document metadata shall be in the lower-right corner of the drawing.

  - For documents, a cover sheet should identify the document title, document number, and revision. A revision block may be on the bottom, or on page 2.

- Ensure your documents are in natural reading order, i.e., top-left to bottom-right. Drawings and spreadsheets, as applicable, should be in landscape mode.

  - Documents must be fully legible and text-searchable.

- No document shall have a file embedded within it. Any atttachments shall be submitted with the original documents file name along with the text “-Att-n” where n is the attachment number. Attachments shall also be identified at the end of the parent document.

- If a document is to be issued VOID (Issue Status: SUP),

  - The document must have a clear watermark on the first page stating “VOID”. Beneath the watermark shall be a reference to the superseding document, if any.

  - The superseding document shall be issued IFR, Revision A as if it were a new document. A stamp or other identifier shall be present on the first page noting the document supersedes the VOID document.

- Documents do not contain hyperlinks.

RE shall email native documents and PDFs to documentcontrol@hanson-inc.com. PDFs must be OCRd and searchable.

### Outgoing

Project personnel - based on the DDM - shall be notified that a new document is available for review or comment. The review process shall be handled via Adobe Cloud. Reviewers will have three days to review a document. At the end of the third day, the review cycle shall be closed.

#### For Information, For Use, Etc

Documents not requiring a review cycle shall be sent via email to appropriate project personnel. The email shall include all documents as listed in the transmittal, hyperlinked, along with required metadata (Email Notifications).

### Incoming

Once the review cycle has been completed, document shall be uploaded to SharePoint as a new version (not revision). Once SharePoint updates have been completed, a notification email (Email Notifications) shall be sent to all appropriate project personnel. At this time, if required, a new revision cycle is to begin with comments incorporated and the document shall undergo another review process of the next revision.

### Email Notifications

When a document has been issued that does not require a comment review cycle, or the comment review cycle has been closed, appropriate project personnel shall be notified of the document’s existence within SharePoint. Every document and revision shall be associated with a transmittal. Transmittal shall clearly identify the transmittal number in the subject line, along with the status of the associated documents.

The body of the email shall contain a table of each documents file name, hyperlinked to the document within the DMS, along with

- Document Title

- Document Revision (Client takes precedence over Company)

- Revision Date

- Issue Status

The body of the email shall conclude with the following formatted text:

THE MOST CURRENT VERSION OF PROJECT DOCUMENTS ARE ON THE PROJECTS RESPECTIVE SHAREPOINT SERVER. USERS OF THESE DOCUMENTS SHOULD ONLY TRUST THE PROJECTS RESPECTIVE SHAREPOINT AS THE OFFICIAL SOURCE. DIGITAL AND PRINTED COPIES OF THIS DOCUMENT STORED FOR ACCESS AND USE ANYWHERE ELSE MAY BE OBSOLETE.

No other information is required.

The email shall be sent to all members as listed in [Document Distribution Matrix].

The email shall be sent from the Hanson Document Control email address (documentcontrol@hanson-inc.com). No emails from individual email addresses shall be sent.

Once the email has been sent it shall be filed away in a subfolder of the inbox.

## Revision and Approval

Every controlled document must have a revision and issue status. Acceptable revisions for Company are identified in Appendix 3.

No revisions are to be skipped. In case of rejection from DC, RE shall make the necessary corrections keeping the revision number consistent and return to DC for processing.

## Distribution of Documents

Per the [Document Distribution Matrix], once a document has been released for transmittal, a review session will begin using Adobe Cloud. All users will receive a link to the document to review, mark up, and make any additional comments to the document.

Project personnel will have three days to review the document. At the end of the third day, the session will be closed and the document shall be uploaded to SharePoint with the Issue Status Code COM for “Comments”. At that time, a new transmittal shall be created notifying all responsible Project personnel of the update with a link to the new documents in SharePoint.

### Adobe Cloud Review

Reviewers of documentation shall have an Adobe account. Users may visit Adobe.com and click the “Sign in” button in the top-right corner of the home page. There is no fee for having an account with Adobe nor is any fee required on the Users end to comment and review documentation. However, Users with a paid Adobe Acrobat subscription may be able to review and comment on documents from their desktop app.

Users are encouraged to bookmark the homepage of the Adobe Acrobate website. From there, Users can click “Documents” in the top navigation bar. On the left hand menu of the next page, under FILES is “Shared by others”. All documents currently in the review cycle and requiring comments/review by User shall be listed here. Note once the comment review cycle closes the document will be removed from this page.

### Bluebeam Sessions

#### Bluebeam Session Structure

- Originator (O) creates the document

- Originator (O) initiates Bluebeam review session per Document Distribution Matrix (DDM)

- Task Manager (TM) and other reviewers participate in simultaneous review session

- Task Manager (TM) finalizes review comments

- Professional of Record (POR) provides final approval

- Originator saves final marked-up document along with audit report to network drive.

#### Standard Timeline for Review Sessions

- Total duration: 5 business days

- Reviewer participation: Days 1-4

- TM finalization: 24 hours prior to session closeout (Day 4)

- POR final approval: Final day (Day 5)

Note: POR may participate throughout the review cycle but has final approval authority.

#### Session Management

- O invites all project team members per DDM

- All reviewers participate simultaneously in one session

- Session prompts TM and other reviewers to begin review cycle

- Subcontractor participation (when applicable): Comment-only access

  - Requires Bluebeam subscription

- Session closeout occurs at predetermined time

#### Audit Trail Requirements

All projects must maintain audit trail of every controlled document:

- Marked-up PDFs with comments saved as controlled documents

  - These shall be identified with a code stamp per Appendix D

- Bluebeam audit trail exports to Excel saved as separate QCR documents

- QCR documents receive independent sequential numbering

##### Audit Trail Management

###### Universal Requirement

All Market projects shall maintain an audit trail of every controlled document.

###### Audit Trail Components

Two components shall be saved as controlled documents per review cycle:

- Marked-up PDFs: Complete document with all accepted review comments visible

- Bluebeam Audit Trail Export: Excel export of review session activity.

###### Quality Control Reports (QCR)

Bluebeam audit trail exports shall be saved as separate QCR documents:

- QCR documents receive independent sequential numbering

- Example: PRJ-PMG-QCR-241216 (audit trail for review session)

- QCR documents are linked to original documents through metadata

###### Documentation Requirements

- Session Completion: When Bluebeam session ends, export audit trail to Excel

- Document Approval: Save marked-up PDF as approved by POR

- Archive Storage: Both components stored per network drive structure

- Metadata Tracking: Critical for linking audit trails to original documents

## Data Inventory

## Appendix A: Document Numbering Schematic

### Format Structure

All Market documents shall follow established numbering formats based on project classification. The numbering schematic provides systematic identification and organization of documents throughout their lifecycle.

#### Class I Projects

Class I projects shall use the following format:

AAAAAAAAA-BBB-CCC-DDDD

Where:

- AAAAAAAAA = Project identifier (9-character alphanumeric string)

- BBB = Discipline code (3-character alphabetic string)

- CCC = Document type code (3-character alphabetic string)

- DDDD = Sequential number (4-digit numeric string, discipline-specific)

#### Class II and Class III Projects

Class II and Class III projects shall use the following format:

AAAAAAAAA -OO-BBB-CCC-DDDD

Where:

- AAAAAAAAA = Project identifier (9-character alphanumeric string)

- OO = Originator code (2-character alphabetic string)

- BBB = Discipline code (3-character alphabetic string)

- CCC = Document type code (3-character alphabetic string)

- DDDD = Sequential number (4-digit numeric string, discipline-specific)

#### Code Separation Requirements

Originator codes, discipline codes, and document type codes shall never share identical codes to prevent ambiguity. The character length restrictions ensure clear distinction between code categories.

#### Sequential Numbering Rules

- Sequential numbers shall be discipline-specific within each document type

- Numbers shall begin at 0001 for each discipline/document type combination

- VOID document numbers shall never be reused under any circumstances

- CAN document numbers shall not be reused for operational simplicity

- Sequential gaps from retired numbers remain permanent in the numbering system

### Market Documents

Market-specific documents shall use the format:

IND-BBB-CCC-DDDD

Where IND identifies the Market business unit and follows the same coding structure as project documents for discipline, document type, and sequential numbering.

## Appendix B: Discipline Codes

The following discipline codes shall be used for all Market projects and documents:

| Code | Description |  |
| --- | --- | --- |
| PMG | Project Management |  |
| CIV | Civil |  |
| ELE | Electrical |  |
| CST | Cost and Planning |  |
| HLT | Health |  |
| SAF | Safety |  |
| ENV | Environment |  |
| SEC | Security |  |
| INS | Instrumentation |  |
| INF | Information Management |  |
| MEC | Mechanical |  |
| PRC | Process |  |
| CPR | Contracting and Procurement |  |

Discipline codes are 3-character alphabetic strings and shall be selected from this approved list only. New discipline codes may be added through formal procedure revision process.

## Appendix C: Document Type Codes

The following document type codes shall be used for all Market projects and documents:

| Code |  | Description |  | Typical Content |
| --- | --- | --- | --- | --- |
| CAL |  | Calculations |  | Equipment calculations, structural calculations, analysis calculations |
| DWG |  | Drawings |  | Arrangement diagrams, block diagrams, layouts, wiring diagrams, general diagrams |
| RPT |  | Reports |  | Analysis reports, equipment reports, inspection reports, performance reports, review reports, test reports |
| SPC |  | Specifications |  | Technical specifications and requirements |
| DAT |  | Data/Lists |  | Data sheets, registers, lists, general data documents |
| PRO |  | Procedures/Manuals |  | Manuals, philosophies, procedures, operational documents |
| PLN |  | Plans/Studies |  | Plans, studies, strategic documents |
| TRM |  | Transmittals/Requests |  | Transmittals, requests, formal communications |
| COR |  | Correspondence |  | Project correspondence, letters, communications |
| CRT |  | Certificates |  | Certificates, certifications, formal attestations |
| TMP |  | Templates |  | Document templates, forms, standardized formats |
| QCR |  | Quality Control Reports |  | Audit trail documentation, review session exports |
| GEN |  | General/Miscellaneous |  | General documents, narratives, miscellaneous items |

Document type codes are 3-character alphabetic strings and shall be selected from this approved list only. New document type codes may be added through formal procedure revision process.

## Appendix D: Return Status Codes

- Code 1: Approved

- Code 2: Approved with comments

- Code 3: Rejected

- Code 4: Information Only

- Code 5: VOID

## Appendix E: Project Class Requirements

|  | ## Class I |  |  | ## Class II | ## Class III |
| --- | --- | --- | --- | --- | --- |
| ## Project Classification | ## R |  |  | ## R | ## R |
| ## EDMS | ## BP |  |  | ## R | ## R |
| ## Network Drive | ## R |  |  | ## R | ## R |
| MDR |  | BP |  | R | R |
| Document Numbering |  | R |  | R | R |

- N/A – Not Applicable

- BP – Best Practice

- R - Required

## Attachment 1: Internal Review Cycle

# Attachment 2: Deliverable Review Cycle